Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 19 July 2026 |
| --- | --- |
| Team ID |  |
| Project Name | Book a Doctor — Healthcare Appointment Booking Platform |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | As a patient/doctor, I can register for the application by entering my name, email, password, and confirming my password. | 2 | High |  |
| Sprint-1 |  | USN-2 | As a user, I receive a success message once registration is complete and I am redirected to the login page. | 1 | High |  |
| Sprint-1 | Login | USN-3 | As a user, I can log into the application by entering my email & password and receive a JWT session token. | 1 | High |  |
| Sprint-1 |  | USN-4 | As a user, my JWT token and role (patient/doctor/admin) are stored so protected routes load the correct dashboard. | 2 | High |  |
| Sprint-1 | Doctor Discovery | USN-5 | As a patient, I can browse the list of admin-approved doctors filtered by specialisation. | 3 | High |  |
| Sprint-1 |  | USN-6 | As a patient, I can view a doctor's profile including experience, fees, address, and available timings. | 2 | High |  |
| Sprint-1 | Doctor Onboarding | USN-7 | As a doctor, I can apply to join the platform by submitting my profile details for admin approval. | 3 | High |  |
| Sprint-1 | Admin Approval | USN-8 | As an admin, I can view a list of pending doctor applications awaiting approval. | 2 | High |  |
| Sprint-1 |  | USN-9 | As an admin, I can approve or reject a doctor's application. | 2 | High |  |
| Sprint-1 | Notifications | USN-10 | As a user, I receive an in-app notification when my doctor application status changes. | 2 | Medium |  |
| Sprint-2 | Appointment Booking | USN-11 | As a patient, I can select an available date & time and book an appointment with a doctor. | 3 | High |  |
| Sprint-2 |  | USN-12 | As a patient, I can upload a relevant medical document while booking an appointment. | 2 | Medium |  |
| Sprint-2 |  | USN-13 | As a patient, I can view my own appointment history and current status (pending/approved/rejected/completed). | 2 | High |  |
| Sprint-2 | Doctor Dashboard | USN-14 | As a doctor, I can view the list of appointment requests booked with me. | 3 | High |  |
| Sprint-2 |  | USN-15 | As a doctor, I can approve or reject a pending appointment request. | 3 | High |  |
| Sprint-2 |  | USN-16 | As a doctor, I can mark a completed consultation as "completed" on the appointment record. | 2 | Medium |  |
| Sprint-2 | Notifications | USN-17 | As a patient, I am notified in-app when my appointment is approved or rejected. | 2 | High |  |
| Sprint-2 | Admin Dashboard | USN-18 | As an admin, I can view all registered users, doctors, and appointments on the platform. | 3 | Medium |  |
| Sprint-3 | Registration | USN-19 | As a user, I can register/sign in through Google OAuth as an alternative to email/password. | 2 | Low |  |
| Sprint-3 | Login | USN-20 | As a user, I can reset my forgotten password via a verification email. | 3 | Medium |  |
| Sprint-3 | Doctor Profile | USN-21 | As an approved doctor, I can edit my own profile, fees, and timings. | 2 | Medium |  |
| Sprint-3 | Appointment Booking | USN-22 | As a patient, I can cancel my own appointment while it is still pending. | 2 | Medium |  |
| Sprint-3 |  | USN-23 | As a patient, I am prevented from double-booking a doctor's slot that is already taken. | 3 | High |  |
| Sprint-3 | Admin Approval | USN-24 | As an admin, I can deactivate or block a user or doctor account that violates platform policy. | 2 | Low |  |
| Sprint-3 | Security | USN-25 | As a developer, protected client routes redirect unauthenticated or wrong-role users away from patient/doctor/admin pages. | 3 | High |  |
| Sprint-3 |  | USN-26 | As a developer, all stored passwords are salted and hashed with bcrypt before being saved to the database. | 2 | High |  |
| Sprint-3 | UI/UX | USN-27 | As a user, the application layout is responsive and usable on mobile and tablet screens. | 1 | Low |  |
| Sprint-4 | Deployment | USN-28 | As a developer, I can deploy the React client and Express API to Render for production use. | 3 | High |  |
| Sprint-4 |  | USN-29 | As a developer, production secrets (JWT_SECRET, MONGO_URI) are configured via environment variables, not hard-coded. | 2 | High |  |
| Sprint-4 | Notifications | USN-30 | As a user, I can mark my notifications as read/seen so they no longer show as new. | 2 | Medium |  |
| Sprint-4 | Admin Dashboard | USN-31 | As an admin, I can see summary counts (total users, doctors, appointments) on my dashboard. | 3 | Low |  |
| Sprint-4 | UI/UX | USN-32 | As a user, I see loading spinners and alert/toast messages for every API action (via Redux alertSlice). | 2 | Medium |  |
| Sprint-4 | Testing | USN-33 | As a developer, I have automated tests covering the authentication and appointment-booking API routes. | 3 | Medium |  |
| Sprint-4 | Documentation | USN-34 | As a developer, the README documents environment variables and setup steps for running client & server. | 1 | Low |  |
| Sprint-4 | File Handling | USN-35 | As a user, uploaded medical documents are served securely through a dedicated static route. | 2 | Medium |  |
| Sprint-4 | QA | USN-36 | As a team, we run a final bug-fixing and QA pass before the release build. | 2 | High |  |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 01 Jun 2026 | 06 Jun 2026 | 20 | 06 Jun 2026 |
| Sprint-2 | 20 | 6 Days | 08 Jun 2026 | 13 Jun 2026 | 20 | 13 Jun 2026 |
| Sprint-3 | 20 | 6 Days | 15 Jun 2026 | 20 Jun 2026 |  |  |
| Sprint-4 | 20 | 6 Days | 22 Jun 2026 | 27 Jun 2026 |  |  |

Velocity:

Across Sprint-1 and Sprint-2, the team completed 20 story points in each 6-day sprint. Let's calculate the team's average velocity (AV) per iteration unit (story points per day):

AV  =  velocity / sprint duration  =  20 / 6  ≈  3.33 story points per day

Burndown Chart:

A burn down chart is a graphical representation of work left to do versus time. It is often used in agile software development methodologies such as Scrum. However, burn down charts can be applied to any project containing measurable progress over time.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts